## Sheet1
SEES PROJECT TIMELINE
Spacial Echolocation Enchancement System
Project Start Date: | 2014-10-14 |  |  | Planned | [6 empty] | Completed
Project End Date: | 2014-12-02 |  |  | In Progress | [6 empty] | Overdue
|  | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Project / Milestone 1 Planning | bar: 14
Milestone 1:
Prototype Design Visuals | bar: 15 to In Progress 20
Progress Report | bar: 15 to In Progress 20
Milestone 2:
Electronics & Software Specifications | bar: In Progress 21 to Overdue 3
Milestone 2 Planning | bar: In Progress 21
Audio Sub-System Research | bar: In Progress 22 to Overdue 3
Audio Sub-System Design | bar: Overdue 28 to Overdue 3
Sensor Electronnics Research | bar: In Progress 22 to Overdue 3
Sensor System Design | bar: Overdue 28 to Overdue 3
Milestone 3:
Experimental Test Data | bar: Overdue 4 to Overdue 17
Milestone 3 Planning / Mid-Project Review | bar: Overdue 4
Software Prototype Construction | bar: Overdue 5 to Overdue 7
Test Protocol Development | bar: Overdue 5 to Overdue 7
Testing | bar: Overdue 8 to Overdue 17
Milestone 4
Full System Specification and Report | bar: Overdue 11 to Overdue 24
Milestone 4 Planning | bar: Overdue 11
Test Data Analysis | bar: Overdue 12 to Overdue 14
System Specification and Report | bar: Overdue 12 to Overdue 24
Project Review | bar: Overdue 25