## Sheet1
SEES PROJECT TIMELINE
Spacial Echolocation Enchancement System
Project Start Date: | 2015-05-07 |  | Team Selection | [6 empty] | Project Form Submitted | [8 empty] | Progress Report 1, Work Log & Milestones | [15 empty] | Work Log & Milestones
Project End Date: | 2015-07-31 |  |  |  | I |  |  |  |  | I | [13 empty] | I | [13 empty] | I
[5 empty] | I |  |  |  |  | I | [7 empty] | Idea Pitch | [5 empty] | I | Idea Pitch | [12 empty] | I |  | Progress Presentation
|  | 1 | [6 empty] | 2 | [6 empty] | 3 | [6 empty] | 4 | [6 empty] | 5 | [6 empty] | 6 | [6 empty] | 7
|  | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28
Project Planning: | bar: 1 11 to 2 19
Assemble Team | bar: 1 11 to 1 14
Establish Project Timeline | bar: 1 11 to 2 19
Submit Project Form | bar: 1 11 to 2 19
Milestone 1: Component Acquisition & Investigation | bar: 2 19 to 4 2
Finalize System Model Decision | bar: 2 19 to 2 22
Acquire Hardware Components | bar: 2 19 to 4 2
Investigate Platform Capabilities | bar: 2 19 to 3 26
Milestone Deliverables:
Progress Report 1 | bar: 3 26 to 4 2
Milestone 2: System Development | bar: 4 2 to 6 16
Build Headset Base Frame | bar: 4 2 to 4 5
Salvage Camera Unit | bar: 4 2 to 6 16
Get Camera Unit Working in Software | bar: 4 2 to 5 9
Establish Audio Signalling Model | bar: 4 2 to 6 16
Milestone Deliverables:
Usable Software&Hardware Prototype | bar: 4 2 to 6 16
|  |  | Work Log & Milestones | [8 empty] | Progress Report 2, Work Log & Milestones | [15 empty] | Work Log & Milestones | [6 empty] | Equipment Loan List | [10 empty] | Final Report
|  |  | I | [13 empty] | I | [13 empty] | I | [6 empty] | I | [9 empty] | I
|  |  | I |  | Progress Presentation | [6 empty] | Progress Pres |  |  |  |  | I |  | Reading Break | [6 empty] | Progress Pres |  |  |  |  | I | [6 empty] | I |  |  | Public Presentation | [6 empty] | I
|  | 6 | [6 empty] | 7 | [6 empty] | 8 | [6 empty] | 9 | [6 empty] | 10 | [6 empty] | 11 | [6 empty] | 12
|  | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2
Milestone 3: System Refinement & User Testing | bar: 6 16 to 8 30
Iterate on Audio Signalling Model | bar: 6 16 to 8 30
Migrate System to Mobile | bar: 6 16 to 7 23
Design User Test Protocol | bar: 6 16 to 7 23
User Testing | bar: 6 16 to 10 14
Milestone Deliverables:
Progress Report 2 | bar: 6 16 to 8 30
Milestone 4: Website Development & Report | bar: 8 30 to 12 31
Design and Implement Website | bar: 8 30 to 9 10
Finalize System Prototype | bar: 8 30 to 11 24
Milestone Deliverables:
Project Report | bar: 8 30 to 12 31
Project Review | bar: 11 21 to 12 31